## Sheet1
| Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6 | Phase 7 | Phase 8
Duration (days)
New Features | Phase 1: User Authentication Robot Show Page
Rails
Models | Phase 1: User Robot
Views | Phase 1: users/new.html.erb session/new.html.erb robots/new.html.erb
Controllers | Phase 1: UsersController (create, new) SessionsController (create, new, destroy) RobotsController (create, new, show)
Backbone
Models
Views
Model/Collection

## Sheet2
Robot Gallery Work Breakdown Structure and Schedule | User Authentication | robot - show robot - index | robot mapview | robot/index filtering tools | comment - create comments - show | like - create likes - show | robot_likes - show | css backbone | add non-critical features
| Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6 | Phase 7 | Phase 8 | Phase 9 | total
duration (days) | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 9.5
Views - rails
users/new.html.erb | bar: Phase 1 to Phase 9
session/new.html.erb | bar: Phase 1 to Phase 9
Models - rails
user | bar: Phase 1 to Phase 9
robot | bar: Phase 1 to Phase 9
comment | bar: Phase 1 to Phase 9
like | bar: Phase 1 to Phase 9
robot_likes join table ? | [10 empty] | name: | Atlas | bar: Phase 1 to Phase 9
Controllers - rails | [10 empty] | manufacturer: | Google
UsersController (create, new) | [10 empty] | description: | humanoid utility robot | bar: Phase 1 to Phase 9
SessionsController (create, new, destroy) | [10 empty] | location: | 124 Market St. | bar: Phase 1 to Phase 9
RobotsController (create, new, show) | bar: Phase 1 to Phase 9
CommentsController (create, new, show) | bar: Phase 1 to Phase 9
LikesController (create, new, show) | bar: Phase 1 to Phase 9
Views - backbone | [10 empty] | name: | mosqui-drone
Navigation Bar | [10 empty] | manufacturer: | Israel | bar: Phase 1 to Phase 9
robots/index | [10 empty] | description: | insectoid spy-bot | bar: Phase 1 to Phase 9
robot/show | [10 empty] | location: | 769 Market St. | bar: Phase 1 to Phase 9
robots/index-mapview | bar: Phase 1 to Phase 9
robots/embedded video (subView of show) | bar: Phase 1 to Phase 9
robot/index filtering tools | bar: Phase 1 to Phase 9
comment/create | bar: Phase 1 to Phase 9
comment/show | bar: Phase 1 to Phase 9
comment/edit | bar: Phase 1 to Phase 9
comment/delete | bar: Phase 1 to Phase 9
like/create-destroy | bar: Phase 1 to Phase 9
robot_likes/show (very similar to robot/list) | bar: Phase 1 to Phase 9
Footer | bar: Phase 1 to Phase 9
Models/Collections - backbone
robot | bar: Phase 1 to Phase 9
comment | bar: Phase 1 to Phase 9
like | bar: Phase 1 to Phase 9
robot_likes join table ? | bar: Phase 1 to Phase 9
Gems/Libraries